## 5.1
D- 5.1 Documents to be Generated |  |  | R- 5.1 Documents ro be Referred
5.1.1 | Appoint individuals to undertake the information management function |  | 5.1.2 | Establish the project's information requirements
| OIR | Organizational information Requirement |  | OIR | Organizational Information Requirements
| REM-A_0 | Information Management Assignment Matrix- (Responsibility Matrix Information Management Activities) |  | PLQ_0 | Plain/Pre-Qualification Questions
| FRA_0 | Functions Responsibilities & Authorities (Individuals List ) |  | PoW_0 | Plan of Work
5.1.2 | Establish the project's information requirements |  | 5.1.3 | Establish the project's information delivery milestones
| USE_0 | BIM Uses Matrix |  | PSC | Project's Schedule from Project Plan
| PIR | Project Information Requirements(Main Document) |  | PoW_0 | Plan of Work (Including key decision points & other milestones)
5.1.3 | Establish the project's information delivery milestones |  | 5.1.4 | Establish the project's information standard
| MIS_0 | Milestone Schedule (List and dates Including detailed description of the information at each key decision point) |  | REM-A_0 | Information Management Assignment Matrix-(In. Man.Activities)
5.1.4 | Establish the project's information standard |  |  | FRA_0 | Functions Responsibilities & Authorities (Individuals List )
| ICN_0 | Information Container Naming Requirements |  | PRS_0 | Procurement Route (Schema & Table)
| COL-S | Collaboration & Modeling & Publishing Standards (within the CDE) |  | COL-PP | Collaboration Process (within the CDE)
| PAT-S | PIM to AIM Transition Standards (Ref.to 5.8.1) | 5.1.5 | Establish the projects information production methods and procedures
| INS_0 | Projects information Standards |  | OIR | Organizational Information Requirements
5.1.5 | Establish the projects information production methods and procedures |  |  | PIR | Project Information Requirements
| QUA_0 | Quality Assurance Manual |  | REM-A_0 | Information Management Assignment Matrix- (Information Man. Act.)
| CCI_0 | Coordination Clash Detection & Issue Management Manual |  | PRS_0 | Procurement Route (Schema & Table)
| DAS_0 | Data Management According to Segregation |  | COL-PP | Collaboration Process (within the CDE)
| SCO_0 | Spatial Coordination (Coordinates & Geo-Location Methods & Procedures | 5.1.6 | Establish the project’s reference information and shared resources
| SCR_0 | Security Requirements |  | OIR | Organizational Information Requirements
| PAT-MP | PIM to AIM Transition Methods and Procedures |  | COL-PP | Collaboration Process (within the CDE)
| COM_0 | CDM/Health & Safety Requirements |  | PIR | Project Information Requirements
| COL-MP | Collaboration & Modeling & Publishing Methods & Procedures (within the CDE) | 5.1.7 | Establish the projects common data environment
| PMP_0 | Project's Information Production Methods and Procedures (MAIN DOCUMENT incl. all generated in this activity) |  | ICN_0 | Information Container Naming Requirements
5.1.6 | Establish the project’s reference information and shared resources |  |  | CLM_0 | Project's Classification System & Metadata- to be generated in the beginning of the activity
| REF_0 | Project’s reference information and shared resources (MAIN DOCUMENT-Including PIT_0, LIB_0, SHR_0) |  | COL-S_0 | Collaboration & Modeling & Publishing Standards (within the CDE)
| PIT_0 | Project Information Table |  | COL-MP_0 | Collaboration & Modeling & Publishing Methods & Procedures (within the CDE)
| LIB_0 | Library Guide & Library Structure in Data Environment | 5.1.8 | Establish the Project's Information Protocol
| SHR_0 | Shared Resources Guide & Shared Resources in CDE |  | RAS_0 | Risk Assessment Requirements (Needs to be generated in the beginning of the activity.)
5.1.7 | Establish the projects common data environment |  |  | TRA_0 | Training Requirements
| CLM_0 | Project's Classification System & Metadata |  | REF_0 | Project’s reference information and shared resources
| CDE_0 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Requirements, COL-MP & COL-S) |  | COL-S_0 | Collaboration & Modeling & Publishing Standards (within the CDE)
5.1.8 | Establish the Project's Information Protocol |  |  | COL-MP_0 | Collaboration & Modeling & Publishing Methods & Procedures (within the CDE)
| AIR | Asset Information Requirements (Including Handover Requirements) |  | PMP_0 | Project's Information Production Methods and Procedures
| INP_0 | Project's Information Protocol |  | INS_0 | Project's Information Standard
|  |  |  | OIR | Organizational Information Requirements

## 5.2
D- 5.2 Documents to be Generated |  |  | R- 5.2 Documents to be Referred
5.2.1 | Establish the appointing party’s exchange information requirements |  | 5.2.1 | Establish the appointing party’s exchange information requirements
| EIR_APOP | Exchange Information Requirements (Appointing Party's) (MAIN DOCUMENT incl. all generated in this activity) |  | OIR | Organizational Information Requirements | MIS_0 | Milestones Schedule
| LOIN_0 | Level of Information Need Manual |  | PIR | Project Information Requirements | INP_0 | Project's Information Protocol
5.2.2 | Assemble reference information and shared resources |  |  | AIR | Asset Information Requirements (Including Handover Requirements) | BUA_0 | BIM Uses Analysis
| PIT_1 | Project Information Table |  | LOIN_0 | Level of Information Need Manual (Needs to be generated in the beginning of the activity.) | PIT_0 | Project Information Table
| LIB_1 | Library Guide & Library Structure in Data Environment |  | LOA_0 | Level of Accuracy Table (Needs to be generated in the beginning of the activity.) | LIB_0 | Library Guide & Library Structure in Data Environment
| SHR_1 | Shared Resources Guide & Shared Resources in CDE |  | RAS_0 | Risk Assessment Requirements | SHR_0 | Shared Resources Guide & Shared Resources in CDE
| REF_1 | Project’s reference information and shared resources (MAIN DOCUMENT-Including PIT_1, LIB_1, SHR_1) |  | CDE-SMP_0 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Req. and COL-S | QUA_0 | Quality Assurance Manual
5.2.3 | Establish tender response requirements and evaluation criteria |  |  | PMP_0 | Project's Information Production Methods and Procedures | CCI_0 | Coordination Clash Detection & Issue Management Manual
| TEN-CR | Tender Response Requirements & Evaluation Criteria (MAIN DOCUMENT) |  | INS_0 | Project's Information Standard | AAP | APOP Asurance Processes (Needs to be available already.)
| CCA_IM | Information Management Capability & Capacity Assessment Form |  | PSC | Project's Schedule from Project Plan | REF_0 | Project’s reference information and shared resources
| CCA_IP | Information Production Capability & Capacity Assessment Form |  | PoW_0 | Plan of Work (Including key decision points & other milestones) | USE_0 | BIM Uses Matrix
| CCA_IT | IT-Information Technology Capability & Capacity Assessment Form | 5.2.2 | Assemble reference information and shared resources
| RAS_1 | Risk Assessment |  | PIT_0 | Project Information Table | REF_0 | Project’s reference information and shared resources
| MOB_I | Delivery team's mobilization plan (Initial-Proposed) to be generated in the beginning of the activity |  | LIB_0 | Library Guide & Library Structure in Data Environment | CDE_0 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Requirements and COL-PP)
5.2.4 | Compile invitation to tender information |  |  | SHR_0 | Shared Resources Guide & Shared Resources in CDE
| TEN | INVITATION TO TENDER PACKAGE (MAIN DOCUMENT-Including EIR_APOP, TEN-CR_0, INP_0, MIS_1, PMP_0, INS_0, REF-1) | 5.2.3 | Establish tender response requirements and evaluation criteria
|  |  |  | RAS_0 | Risk Assessment Requirements | EIR_APOP | Exchange Information Requirements (Appointing Party's)
|  |  |  | ACR_0 | Acceptance Criteria Manual | REM-A_0 | Information Management Assignment Matrix-(In. Man.Activities)
|  |  |  | MOB_I | Delivery team's mobilization plan (Initial-Proposed) to be generated in the beginning of the activity
|  |  | 5.2.4 | Compile invitation to tender information
|  |  |  | EIR_APOP | Exchange Information Requirements (Appointing Party's) | PMP_0 | Project's Information Production Methods and Procedures
|  |  |  | TEN-CR_0 | Tender Response Requirements & Evaluation Criteria | INS_0 | Project's Information Standard
|  |  |  | INP_0 | Project's Information Protocol | REF_1 | Project’s reference information and shared resources
|  |  |  | MIS_1 | Milestones Schedule (List and dates Including detailed description of the information at each key decision point)

## 5.3
R- 5.3 Documents to be referred
5.3.1 | Nominate individuals to undertake the information management function
| OIR | Organizational Information Requirements | EIR_APOP | Exchange Information Requirements (Appointing Party's)
| PRS_0 | Procurement Route (Schema & Table) | FRA_0 | Functions Responsibilities & Authorities (Individuals List )
| REM-A_0 | Information Management Assignment Matrix
5.3.2 | Establish the delivery team's (pre-appointment) BIM execution plan
| FRA_1 | Functions Responsibilities & Authorities (Individuals List ) | USE_0 | BIM Uses Matrix
| PMP_0 | Project's Information Production Methods and Procedures | BUA_0 | BIM Uses Analysis
| CCI_1 | Coordination Clash Detection & Issue Management Manual | PRS_0 | Procurement Route (Schema & Table)
| LOIN_0 | Level of Information Need Manual | INP_0 | Project's Information Protocol
| EIR_APOP | Exchange Information Requirements (Appointing Party's) | COL-S_0 | Collaboration & Modeling & Publishing Standards (within the CDE)
| REM-A_1 | Information Management Assignment Matrix-(Resp. Matrix Infor. Man. Act.) | COL-MP_0 | Collaboration & Modeling & Publishing Methods & Procedures (within the CDE)
| INS_0 | Project's Information Standard | ICN_0 | Information Container Naming Requirements
| QUA_1 | Quality Assurance Manual
5.3.3 | Assess each task team capability and capacity
| TRA_0 | Training Requirements | CCA_IM | Information Management Capability & Capacity Assessment Form
| PMP_1 | Project's Information Production Methods and Procedures | CCA_IP | Information Production Capability & Capacity Assessment Form
| TEN-CR_0 | Tender Response Requirements & Evaluation Criteria | CCA_IT | IT-Information Technology Capability & Capacity Assessment Form
5.3.4 | Establish the delivery team's capability and capacity
| TT-IDS_0 | Task Teams' Information Delivery Strategies | RAS_1 | Risk Assessment Requirements
| TT-CCA_0 | Capability and capacity assessment of Task Teams
5.3.5 | Establish the delivery team’s mobilization plan
| DTCC_0 | Delivery Team's Capability and Capacity Assessment | SCH-IT_0 | Schedule of Software, Hardware & IT
| PMP_1 | Project's Information Production Methods and Procedures | REM-A_2 I | Information Management Assignment Matrix
| CDE_0 | Project's CDE Structure, Standards, Methods, Procedures | EIR_APOP | Exchange Information Requirements (Appointing Party's)
| DT-IDS_0 | Delivery team’s information delivery strategy | TRA_0 | Training Requirements
| FRA_1 | Functions Responsibilities & Authorities (Individuals List ) | PRS_1 | Procurement Route (Schema & Table)
| REM-A_2 | Information Management Assignment Matrix- (Responsibility Matrix Information Management Activities) | HLRM_0 | Delivery team’s High Level Responsibility Matrix
| MOB_I | Delivery team's mobilization plan (Initial-Proposed)
5.3.6 | Establish the delivery team’s risk register
| EIR_APOP | Exchange Information Requirements (Appointing Party's) | DT-IDS_0 | Delivery team’s information delivery strategy
| MIS_1 | Milestones Schedule (List and dates Including detailed description of the information at each key decision point) | DTCC_0 | Delivery Team's Capability and Capacity Assessment
| INP_0 | Project's Information Protocol | INS_1 | Project's Information Standard
| RAS_0 | Risk Assessment Requirements | PMP_1 | Project's Information Production Methods and Procedures
5.3.7 | Compile the delivery team's tender response
| PRE-BEP | Delivery team’s Pre-appointment BIM execution plan | MOB_0 | Delivery Team's Mobilization Plan
| DTCC_0 | Delivery Team's Capability and Capacity Assessment | INP_0 | Project's Information Protocol
| DRR_0 | Delivery team’s Risk Register (Information delivery risk assessment)
D- 5.3 Documents to be Generated
5.3.1 | Nominate individuals to undertake the information management function
| FRA_1 | Functions Responsibilities & Authorities (Individuals List ) (Updated as per this activity by Prospective Lead Appointed Party) | PRS_1 | Procurement Route (Schema & Table) (Updated as per this activity by Prospective Lead Appointed Party)
| REM-A_1 | Information Management Assignment Matrix-(Responsibility Matrix Information Management Activities) (Updated as per this activity by Prospective Lead Appointed Party)
5.3.2 | Establish the delivery team's (pre-appointment) BIM execution plan
| PRE-BEP | Delivery team’s Pre-appointment BIM execution plan (MAIN DOCUMENT incl. all generated in this activity) | BUA_1 | BIM USES ANALYSIS
| CCI_2 | Coordination Clash Detection & Issue Management Manual | PMP_1 | Project's Information Production Methods and Procedures
| LOIN_1 | Level of Information Need Manual | INS_1 | Project's Information Standard
| FSB_0 | Federation Strategy & Information Container Breakdown Structure | SCH-IT_0 | Schedule of Software, Hardware & IT
| HLRM_0 | Delivery team’s High Level Responsibility Matrix | COL-S_1 | Collaboration&Modeling&Publishing Standards (within the CDE)
| DT-IDS_0 | Delivery team’s information delivery strategy | PRS_1 | Procurement Route (Schema & Table)
| COL-MP_1 | Collaboration & Modeling & Publishing Methods & Procedures (within the CDE) | ICN_1 | Information Container Naming Requirements
| QUA_2 | Quality Assurance Manual | USE_1 | BIM Uses Matrix
5.3.3 | Assess each task team capability and capacity
| TT-IDS-0 | Task Teams' Information Delivery Strategies | TT-CCA-1 | Capability and capacity assessment of Task Team-1
5.3.4 | Establish the delivery team's capability and capacity
| REM-A_2 | Information Management Assignment Matrix (Updated as per this activity by Prospective Lead Appointed Party) | DTCC_0 | Delivery Team's Capability and Capacity Assessment
5.3.5 | Establish the delivery team’s mobilization plan
| CDE_1 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Requirements and COL-PP) -(Data Exchange Process Update) | MOB_0 | Delivery Team's Mobilization Plan
5.3.6 | Establish the delivery team’s risk register
| DRR_0 | Delivery team’s Risk Register (Information delivery risk assessment)
5.3.7 | Compile the delivery team's tender response
| DTTR | Delivery team’s Tender Response (Incl. PRE-BEP, DRR, DTCC, MOB)
| INP_1 | Project's Information Protocol (Updated as per previous activities)

## 5.4
R- 5.4 Documents to be referred
5.4.1 | Confirm the delivery team's BIM execution plan
| OIR | Organizational Information Requirements | SUP_LEAP_0 | Supporting Information for LEAP
| REM-A_2 | Information Management Assignment Matrix | TRA_0 | Training Requirements
| CCI_2 | Coordination Clash Detection & Issue Management Manual | ACR_0 | Acceptance Criteria Manual
| PLQ_0 | Plain/Pre-Qualification Questions | SCR_0 | Security Requirements
| FRA_1 | Functions Responsibilities & Authorities (Individuals List ) | PAT-MP_0 | PIM to AIM Transition Methods & Procedures
| LOIN_1 | Level of Information Need Manual | CLM_0 | Project's Classification System
| PIR | Project Information Requirements | COL-S_1 | Collaboration & Modeling & Publishing Standards (within the CDE)
| CDE_1 | Project's CDE Structure, Standards, Methods, Procedures (In. Sec. Req.& COL-PP) | REF_1 | Project’s reference information and shared resources
| DT-IDS_0 | Delivery team’s information delivery strategy | EIR_APOP | Exchange Information Requirements (Appointing Party's) (MAIN DOCUMENT incl. all generated in this activity)
| SCH-IT_0 | Schedule of Software, Hardware & IT | TEN-CR_0 | Tender Response Requirements & Evaluation Criteria
| LOA_0 | Level of Accuracy | USE_1 | BIM Uses Matrix
| RAS_0 | Risk Assessment Requirements | MOB_0 | Delivery Team's Mobilization Plan
| SCO_1 | Spatial Coordination (Coordinates & Geo-Location) Methods & Procedures | DTCC_0 | Delivery Team's Capability and Capacity Assessment
| DAS_1 | Data Management According to Segregation | DRR_0 | Delivery team’s Risk Register (Information delivery risk asses.)
| TT-IDS-0 | Task Teams' Information Delivery Strategies | BUA_1 | BIM Uses Analysis
| COL-MP_1 | Collaboration & Modeling & Publishing Methods & Procedures (within the CDE) | PIT_1 | Project Information Table
| PRE-BEP | Delivery team’s Pre-appointment BIM execution plan | PRS_1 | Procurement Route (Schema & Table)
| AIR | Asset Information Requirements | TT-CCA-0 | Capability and capacity assessment of Task Team
| INP_1 | Project's Information Protocol | PAT-S_0 | PIM to AIM Transition Standards
| QUA_2 | Quality Assurance Manual | SCR_0 | Security Requirements
| MIS_1 | Milestones Schedule | CDM_0 | Health and Safety Requirements
| ICN_1 | Information Container Naming Requirements | LIB_1 | Library Guide & Library Structure in Data Environment
| PMP_1 | Project's Information Production Methods and Procedures | SHR_1 | Shared Resources Guide & Shared Resources in CDE
| INS_1 | Project's Information Standard | FSB_0 | Federation Strategy&Information Container Breakdown Structure
| HLRM_0 | Delivery team’s High Level Responsibility Matrix | PAT-S_0 | PIM to AIM Transition Standards
| MOB_0 | Delivery Team's Mobilization Plan
5.4.2 | Establish the delivery team’s detailed responsibility matrix
| MIS_2 | Milestones Schedule | FRA_2 | Functions Responsibilities & Authorities (Individuals List )
| HLRM_1 | Delivery team’s High Level Responsibility Matrix | CDE_2 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Requirements and COL-PP)
| PMP_2 | Project's Information Production Methods and Procedures | INS_2 | Project's Information Standard
| FSB_1 | Federation Strategy & Information Container Breakdown Structure | PRS_2 | Procurement Route (Schema & Table)
| REM-A_3 | Information Management Assignment Matrix-(Responsibility Matrix Information Management Activities) | DRM_0 | Delivery team’s detailed responsibility matrix (Template)
5.4.3 | Establish the lead appointed party’s exchange information requirements
| EIR-APOP | Exchange Information Requirements (Appointing Party's) | OIR | Organizational Information Requirements
| LOIN_2 | Level of Information Need Manual | PIR | Project Information Requirements
| LOA_1 | Level of Accuracy Table | AIR | Asset Information Requirements
| PMP_2 | Project's Information Production Methods and Procedures | PSC | Project's Schedule from Project Plan
| REF_1 | Project’s reference information and shared resources | RAS_1 | Risk Assessment Requirements
| SUP-APP | Supporting Information for APP | ACR_1 | Acceptance Criteria Manual
| QUA_3 | Quality Assurance, Coordination & Issue Management Manual | PoW_1 | Plan of Work (Including key decision points & other milestones)
| INS_2 | Project's Information Standard | MIS_2 | Plan of Work (Including key decision points & other milestones)
| INP_2 | Project's Information Protocol
5.4.4 | Establish the task information delivery plan(s)
| MIS_2 | Milestones Schedule | PSC | Project's Schedule from Project Plan
| EIR-LEAP | lead appointed party’s exchange information requirements | PoW_1 | Plan of Work (Including key decision points & other milestones)
| ICN_2 | Information Container Naming Requirements
5.4.5 | Establish the master information delivery plan
| DRM_1 | Delivery team’s detailed responsibility matrix | PMP_2 | Project's Information Production Methods and Procedures
| CDE_2 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Req.&COL-PP) | TIDP_1…n | Task Information Delivery Plans
5.4.6 | Complete lead appointed party’s appointment documents
| EIR_APOP | Exchange Information Requirements (Appointing Party's) | BEP_0 | Delivery Team's Post Appointment BEP
| INS_2 | Project's Information Standard | MIDP_0 | Master information delivery plan
| INP_1 | Project's Information Protocol
5.4.7 | Complete appointed party’s appointment documents
| EIR-LEAP | Lead appointed party’s exchange information requirements | BEP_0 | Delivery Team's Post Appointment BEP
| INS_2 | Project's Information Standard | TIDP_1…n | Task Information Delivery Plans
| INP_1 | Project's Information Protocol
D- 5.4 Documents to be Generated
5.4.1 | Confirm the delivery team's BIM execution plan
DOCUMENTS TO BE GENERATED (as Annex, Appendix or Section Inside BEP) | BEP_0 | Delivery Team's Post Appointment BEP (MAIN DOCUMENT) | DTCC_1 | Delivery Team's Capability and Capacity Assessment
| CDE_2 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Requirements and COL-PP) -(Data Exchange Process Update) | DT-IDS_1 | Delivery team’s information delivery strategy
| INS_2 | Project's Information Standard | SCH-IT_1 | Schedule of Software, Hardware & IT
| LOA_1 | Level of Accuracy | PIT_2 | Project Information Table
| SCO_2 | Spatial Coordination (Coordinates & Geo-Location) Methods & Procedures | TEN-CR_1 | Tender Response Requirements & Evaluation Criteria
| DAS_2 | Data Management According to Segregation | LIB_2 | Library Guide & Library Structure in Data Environment
| CCI_3 | Coordination Clash Detection & Issue Management Manual | SHR_2 | Shared Resources Guide & Shared Resources in CDE
| DT-IDS_1 | Delivery Team's Imformation Delivery Strategy | ICN_2 | Information Container Naming Requirements
| TT-CCA_1 | Capability and Capacity Assessment of Task Teams | PAT-S_1 | PIM to AIM Transition Standards
| COL-MP_2 | Collaboration & Modeling & Publishing Methods & Procedures (within the CDE) | SCR_1 | Security Requirements
| TT-IDS-1 | Task Teams' Information Delivery Strategies | QUA_3 | Quality Assurance Manual
| FRA_2 | Functions Responsibilities & Authorities (Individuals List ) | CDM_1 | Health and Safety Requirements
| PRS_2 | Procurement Route (Schema & Table) | RAS_1 | Risk Assessment Requirements
| SUP_LEAP_1 | Supporting Information for LEAP | DRR_1 | Delivery Team's Risk Register
| REF_2 | Project’s reference information and shared resources | FSB_1 | Federation Strategy & Information Container Breakdown Structure
| MIS_2 | Milestones Schedule | INP_2 | Project's Information Protocol
| TRA_1 | Training Requirements | MORE-TMP | Mobilization of resources report template (Ref.to 5.5.1)
| CLM_1 | Project's Classification System | CR-TT-TMP | Task Team's Access Check Report Template (Ref.to.5.6.1)
| PMP_2 | Project's Information Production Methods and Procedures | PAR-TMP | PIM to AIM Requirements Template (Ref.to 5.8.1)
| PAT-MP_1 | PIM to AIM Transition Methods & Procedures | RLL-TMP | Lessons learned record (template Ref.to.5.8.2)
| COL-S_2 | Collaboration & Modeling & Publishing Standards (within the CDE) | PLQ_1 | Plain/Pre-Qualification Questions
| REM-A_3 | Information Management Assignment Matrix-(Responsibility Matrix Information Management Activities) (Updated as per this activity and REM-B-1 by LEAP | MOB_1 | Delivery Team's Mobilization Plan
| HLRM_1 | Delivery team’s High Level Responsibility Matrix | IDM | Information Delivery Manual
| USE_2 | BIM Uses Matrix | EIR-LEAP-TMP | Lead Appointed Party's Exchange Information Requirements Template (Ref.to5.4.3)
| CHL | Change Log Template | PMP-RR-TMP | Project's Information Production Methods & Procedures Test Report Temp.(Ref.to 5.5.2)
| CLAM | Clash Detection Matrix | IRR-TT-TMP | Task Team's Information Review (by LEAP) Report Template (Ref.to.5.6.4)
| ACR_1 | Acceptance Criteria Manual | TTS-RR-TMP | Task Teams Submittals Review Report Template (Ref.to.5.7.2)
| CCA_IM | Information Management Capability and Capacity Assessment Form | SBL-TMP | Submittal List Templates (Ref.to.5.7.1 & 3)
| TIDP-TMP | Task Information Delivery Plan Template | * | Templates as per ISO 19650-3
| BUA_2 | BIM Uses Analysis | MOIR-TMP | Mobilization of information technology report template (Ref.to 5.5.2)
| LOIN_2 | Level of Information Need Manual | QUA-TT-TMP | Task Team's Quality Assurance Check Report Template (Ref.to.5.6.3)
| CCA_IP | Information Production Capability and Capacity Assessment Form | IMR-DT-TMP | Delivery Team's Information Model Review Report Template (Ref.to.5.6.5)
| CCA_IT | Information Technology Capability and Capacity Assessment Form | PIM-RR-TMP | PIM Review Report Template (Ref.to.5.7.4)
| MIDP_0 | Master Information Delivery Plan Initial Version (Template) | CLL-TMP | Capture lessons learned (template Ref.to.5.8.2) Capture lessons learned document will be updated at the end of each main phase
| DRM_0 | Delivery team’s detailed responsibility matrix (Template)
|  | As Annex = Red Color Example: DRM_0 | As Appendix = Purple Color Example: CLL-TMP | As Section Inside BEP = Blue Color Example: SCR_1
5.4.2 | Establish the delivery team’s detailed responsibility matrix
| DRM_1 | Delivery team’s detailed responsibility matrix
5.4.3 | Establish the lead appointed party’s exchange information requirements
| EIR-LEAP | lead appointed party’s exchange information requirements (Main Document) | SUP-APP | Supporting Information for APP
5.4.4 | Establish the task information delivery plan(s)
| TIDP_n | Task Team n's Task Information Delivery Plan
5.4.5 | Establish the master information delivery plan
| MIDP_0 | Master information delivery plan
5.4.6 | Complete lead appointed party’s appointment documents
| L-APD | Lead appointed party’s appointment documents
5.4.7 | Complete appointed party’s appointment documents
| A-APD | Appointed party’s appointment documents

## 5.5
D- 5.5 Documents to be Generated
5.5.1 | Mobilize resources
| MORE | Mobilization of resources report
5.5.2 | Mobilize information technology
| CDE_3 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Requirements and COL-PP)
| INS_3 | Project's Information Standard
| MOIR | Mobilization of information technology report
5.5.3 | Test the project’s information production methods and procedures
| LIB_3 | Library Guide & Library Structure in Data Environment
| SHR_3 | Shared Resources Guide & Shared Resources in CDE
| RES_3 | Project’s reference information and shared resources
| FSB_2 | Federation Strategy & Information Container Breakdown Structure
| PMP_RR | Project's Information Production Methods and Procedures Test Report
| PMP_3 | Project's Information Production Methods and Procedures
R- 5.5 Documents to be referred
5.5.1 | Mobilize resources
| MOB_1 | Delivery Team's Mobilization Plan
| TRA_1 | Training Requirements (Ref.to. 5.5.1)
| DTCC_1 | Delivery team’s capability and capacity assessment
5.5.2 | Mobilize information technology
| MOB_1 | Delivery Team's Mobilization Plan
| INS_2 | Project's Information Standard
| PMP_2 | Project's Information Production Methods and Procedures
| SCH-IT_1 | Schedule of Software, Hardware & IT
| CDE_2 | Project's CDE Structure, Standards, Methods, Procedures (Incl. Security Requirements and COL-PP)
5.5.3 | Test the project’s information production methods and procedures
| LIB_2 | Library Guide & Library Structure in Data Environment
| SHR_2 | Shared Resources Guide & Shared Resources in CDE
| RES_2 | Project’s reference information and shared resources
| FSB_1 | Federation Strategy & Information Container Breakdown Structure
| PMP_2 | Project's Information Production Methods and Procedures